## Slide 1: PROJECT MANAGEMENT SKILLS FOR LIFE®
Presenter Name
  Dd MM YYYY
Notes: Instructor’s notes
Introductions of the instructor and the team
As the instructor, speak for about five minutes about your background. If you are a PMP, provide background on PMI and, if you are a member, the local PMI chapter.
Provide time to conduct class introductions, allowing a few minutes for each person to talk about their background .
Explain how the Project Management Skills for Life document is designed and the expectations of the course content.
Explain that each section will have terms and definitions of basic project management terms.

## Slide 2: WHAT IS PROJECT MANAGEMENT?

## Slide 3: What is Project Management?
Why is project management important?
How do unidentified risks impact the outcome of the project?
Who should be responsible for tasks?
Can projects be divided into multiple projects or phases?
Notes: Instructor’s notes
Discuss the questions with the class and provide further explanation
Identify risks early in the planning phase and conduct a session with the team to discover any risks for the project. Document and develop a list of risks. Explain what could happen to the outcome of the project if risks are not identified early in the project. Unidentified risks could cause schedule delays, added costs for redesign and/or the project may not be able to be completed due to resources, equipment, or materials available.
The project manager should assign tasks based on experience and availability to complete tasks on time.
Explain that some projects will take too long to develop or that the funds are unavailable for the project at this time. It is easier to estimate a project with a shorter timeframe.
PMBOK Terms and Definitions
Project Management – The application of knowledge, skills, tools and techniques to project activities to meet the project requirements.
Project Activities (also referred to as tasks) – A component of work performed during the course of the project.
Project Requirement – A condition or capability that must be met or possessed by a system, product, service, result or component to satisfy a contract, standard, specification or other formally imposed documents. Requirements include the quantified and documented needs, wants and expectations of the sponsor, customer and other stakeholders.

## Slide 4: Triple Constraint Diagram
TIME
COST
SCOPE & QUALITY
Notes: Instructor’s Notes
Explain the Triple Constraint Diagram of time, cost, scope and quality.
The Project Manager’s responsibility is to juggle time, cost, and scope of the project.

## Slide 5: Class Exercise: Human Bingo
B | I | N | G | O
Is allergic to cats | Has two or more sisters | Is a twin | Has a tattoo | Is a vegetarian
Has been to Mexico | Is allergic to dairy | Is allergic to nuts | Is an only child | Has two or more brothers
Has been to Europe | Is afraid of spiders | FREE SPACE | Plays softball or baseball | Has a dog
Plays tennis | Has a cat | Has lived on a farm | Plays soccer | Can stand on his/her head
Plays golf | Has been to Canada | Plays video games | Is afraid of heights | Has a brother AND a sister
Notes: Instructor’s Notes
The BINGO card for this exercise is included in the Appendix of the Project Management Skills for Life document. Allow 10-15 minutes to complete. Instructors are encouraged to adjust the items in each space to better fit the audience (for example, in working with children, “has a tattoo” might be switched to “favorite color is green” or something else age-appropriate).
Objective: The purpose of the game is to have everyone meet each other.
Distribute one BINGO card to each participant.
Participants mingle and try to find individuals who meet the criteria in the squares on the BINGO card. When an individual meets one of the criteria, they sign the square that applies (i.e. a person who is allergic to cats would sign the “Is allergic to cats” at the top of column B. BINGO is achieved by getting five signatures in a row, arranged vertically, horizontally, of diagonally.
The game works best if participants can only sign one box on each person’s card, but this rule may need to be modified for small groups.
The game is complete when there is a top winner, top three winners, or when 10-15 minutes has lapsed.
Ask the team what they learned new about someone in the room. Usually, some people already know each other and learn something new about that person or this is an opportunity to be introduced in a simple interesting approach.

## Slide 6: WHAT IS A PROJECT?

## Slide 7: What is a Project?
A project is a temporary endeavor with a definite beginning and end,
and
It creates or produces a unique product, service or result
What are the key components of a successful project?
Notes: Instructor’s Notes
Explain a project and provide some examples.
Identify and discuss key components of a successful project. Two points to include:
The importance of completing the project on time
The importance of obtaining sponsor approval at the completion of the project

## Slide 8: What is a Project?
Exercise 1 in the Project Management Skills for Life Document
Exercise 1 and Discussion
Notes: Instructor Notes
Exercise 1: This exercise can be found in the Project Management Skills for Life document. Discuss with the team what makes a project successful. Allow 10 minutes for this exercise
Objective: To list 6 projects and the deliverables of successful projects.
As a group activity
Divide into teams
Appoint someone to document points
Identify six projects that you have worked on and list deliverables
Discuss why these projects were successful? If not, why were they not.
PMBOK Terms and Definitions
Project – is a temporary endeavor undertaken to create a unique product, service or result.
Deliverable – Any unique and verifiable product, result or capability to perform a service that must be produced to complete a process, phase, or project. Often used more narrowly in reference to an external deliverable, which is a deliverable that is subject to approval by the project sponsor or customer.

## Slide 9: WHAT IS A PROJECT MANAGER?

## Slide 10: Project Manager Discussion
What are some of the responsibilities of a Project Manager?
Notes: Instructor’s Notes
Explain or discuss responsibilities of a project manager
Work with the team to develop a schedule and discuss potential risks
Communicate with all stakeholders about the status of the project
Conduct weekly or monthly meetings to discuss issues and risks
PMBOK Terms and Definitions
Project Manager – The person assigned by the performing organization to achieve the project objectives

## Slide 11: Project Manager Discussion
How is a Project Manager selected or appointed?
Notes: Instructor’s Notes
Discuss with the team
A common question is how project managers get selected or appointed.
Explain to the class that a project manager has previous background working on similar projects, is a great organizer and strategic planner. This person may like detail work, and normally possesses excellent verbal and written skills. They feel comfortable making presentations and providing project status reports to all stakeholders. This person is a team player and has leadership skills.

## Slide 12: WHAT IS A STAKEHOLDER?

## Slide 13: What is a Stakeholder?
Someone who has a positive or negative impact on the project and can influence the expectations and deliverables
Examples of stakeholders: customers, suppliers, vendors, end-users, team members, and project sponsor
Who were the stakeholders on a project you worked on previously? Who will they be on your next project?
Notes: Instructor’s Notes
Explain how a stakeholder can have positive and negative impacts on the project. Provide some examples.
Provide some examples of stakeholders – customers, suppliers, vendors, end-users, team members and sponsor.
Conduct discussion with the group about who stakeholders were on a previous project. How about their next project?
PMBOK Terms and Definitions
Stakeholder – persons and organizations such as customers, sponsors, performing organization and the public, that are actively involved in the project or whose interests may be positively or negatively affected by execution or completion of the project. They may also exert influence over the project and its deliverables

## Slide 14: WHAT IS A SPONSOR?

## Slide 15: What is a Sponsor?
An individual who provides support or obtains funding for the project
Someone who has a vested interest in the project
Examples of Sponsors
  Member of the management team
  Board of Director or association member
  Client or customer
Notes: Instructor’s Notes
Explain that a sponsor is a person who supports and provides funding for the project. Someone who has a vested interest in the project.
Provide additional examples of sponsors and ask the group for other examples
PMBOK Terms and Definitions
Sponsor – the individual or group within or external to the performing organization that provides the financial resources, in cash or kind, for the project.

## Slide 16: WHAT IS A TEAM MEMBER?

## Slide 17: What is a Team Member?
Important Characteristics of a Project Team
Individuals who are appointed, selected, or volunteer to work together on a project
Individuals who have diverse skills and talents to complete tasks and will provide expertise to make project decisions
Encourage mentoring with team members during the project
Notes: Instructor’s Notes
Explain how project teams are appointed, selected, or volunteer to work on different aspects of the project
It is important to assign tasks according to talents to bring strength to the project.
Encourage the more experience team members to provide assistance to the other members who need help.
PMBOK Terms and Definitions
Team members – All the project team members, including the project management team, the project manager and for some projects the sponsor.

## Slide 18: Team Organizational Chart
Sponsor
Project Manager
Stakeholders
Team Members
Individual who provides support and/or obtains funding for the project. Someone who has a vested interest in the project.
Works with the team to develop a schedule and discuss potential risks. Responsible for ensuring the project is completed on time, within budget, and on schedule.
Appointed individuals and/or volunteers who work together to complete project tasks and deliverables.
Individuals or organizations that have an interest, either positive or negative, in the project’s execution and outcomes.
Notes: Instructor’s Notes
Review the team structure – sponsor, project manager, team members and stakeholder/customer.

## Slide 19: Discussion
Team Directory Template
Notes: Instructor’s Notes
Exercise – Explain why the team directory helps the project manager and the team.
The team directory template is an example and can be modified to fit team needs. It is designed for team members but could be a directory for suppliers, vendors or customers.
Explain the components of the template, which includes all team members, work phone, home phone, cell phone, email address and other important information.

## Slide 20: Class Exercise
Team Conflict and Customer Conflict
Team Conflict
Customer Conflict
The requirements are not clear from the customer
The customer delays making important decisions on critical issues
Who will deliver unfavorable news to the customer if the need arises?
As a large group or in smaller teams, discuss possible solutions to the scenarios below:
Team members are not completing assigned tasks
Team members are not completing tasks on time
Team members are unmotivated to complete tasks
Notes: Instructor’s Notes
Exercise with team to discuss team and customer conflicts.
Divide into teams and discuss possible solutions.
Review team conflict:
Why if team members are not completing the tasks
Team members are late with their tasks
Team members are unmotivated to complete tasks
Review Customer Conflict:
The requirements are not clear from the customer
The customer delays making important decisions on critical issues
Decide who will deliver the news to the customer if it is not favorable

## Slide 21: Project Team Discussion
Team Conflict and Customer Conflict
When will the team meet (weekly, bi-weekly, monthly)?
Who will set the agenda and organize the meeting times?
How will the team make decisions?
Who will take and distribute meeting minutes?
How will the team handle changes?
How will the team resolve conflicts and ensure tasks are completed?
Who will talk to the customer?
Who will report project status to all stakeholders?
Notes: Instructor Notes
Discuss rules and standards with the team. These are some suggestions and the team may think of other rules that could apply.
Review with the team.

## Slide 22: Project Team Discussion
Solutions to Team Conflicts
Notes: Instructor’s Notes
Explain that the project manager needs to:
Clarify with or mentor team members to ensure that they clearly understand their assignments;
Make sure that team members understand the importance of their tasks and that other tasks are dependent on this task being completed first;
Provide positive feedback and show appreciation

## Slide 23: Project Team Discussion
Solutions to Customer Conflicts
Notes: Instructor’s Notes
Obtain feedback during the meeting and status reports
Stress to the team and customer how critical it is to communicate any issues during the status meetings, or at least to the project manager. Follow up by email or phone.
The project manager or sponsor should communicate any delays or issues to the customer. Provide an explanation with the updated information. Document findings on project templates.

## Slide 24: PROJECT MANAGEMENT PROCESSES

## Slide 25: CHAPTER 1: INITIATING PROCESS

## Slide 26: Initiating Process
Determine and decide what product or service is being developed
Collaborate and clarify the project need
Assign or appoint a project manager and sponsor
Gather any information to help understand the requirements of the project by answering the what, when, who, why, where and how questions
Develop the project charter
Notes: Instructor’s Notes
Explain the Initiating Process.

## Slide 27: Initiating Process
Answering a few basic questions helps guide a project from start to finish:
Why?
Who?
What?
When?
Where?
How?
Notes: Instructor’s Notes
Explain and discuss:
Why is the project being initiated? (The project stakeholders should discuss and agree upon the answer for this question.)
Who is this work being done for? Who is the project sponsor and who are the project stakeholders that might use the final product, service, or results?
What are we going to deliver? What work do we need to complete; what resources and funds do we need to produce these deliverables?
When will we produce these deliverables? When will the stakeholders review them? When will the project sponsor approve and accept the final project outcome?
Where will the deliverables be used?
How are we going to achieve the project’s goal and objectives? How will success be measured?
If time permits, consider discussing the similarities and differences between a two different types of projects, such as creating a new webpage and a Halloween party or youth dance.

## Slide 28: Initiating Process
How would you answer the Why, Who, What, When, Where, and How questions for a project you are about to work on or have worked on recently? Use the examples on page 18 of the manual to help you get started.
Exercise 2
Why | 
Who | 
What | 
When | 
Where | 
How | 
Notes: Instructor Notes
Exercise 2 – This exercise can be found on page 15 of the Project Management Skills for Life document. Think about a project you are about to work on or may have previously completed. How would you respond to the Why, Who, What, When, Where and How questions. This can be a group or individual exercise. Allow 10 minutes to complete.
Objective: Individuals respond to the Why, Who, What, When, Where and How questions.
As a group activity
Divide into teams
Appoint someone to document points
Identify the What – When – Who – Why – Where – How
If the individuals have different answers to the questions and they are working on the same project, discuss why. Explain the importance of everyone agreeing to the answers to the questions.

## Slide 29: Project Charter
Documents the answers to the project Why, Who, What, Where, When and How questions
Supported and approved by the sponsor
Provides the project manager authorization to start the project
Notes: Instructor’s Notes
Talk about how to develop a project charter and how the why, who, what, where, when and how questions are related to the project charter.
Explain how this document is the formal document that authorizes the beginning of the project work.
Review the elements of a project Charter and what should be included in each.
Refer to the Project Charter/Scope Statement Template in the Appendix.

## Slide 30: Project Charter
Using the template found on pages 53–54 of the manual and your answers to the Why, Who, What, When, Where, and How questions, create a project charter.
Exercise 3: Write a Project Chapter
Notes: Instructor’s Notes
Exercise 3: This exercise can be found in the Project Management Skills for Life document. You may want to refer to the project charter found in the Appendix. Discuss with the team the writing of a project charter. Allow 15 minutes for this group exercise.
Objective: Discuss creating a project charter and explain the tie between the what, when, who, why, where, and how questions and the project charter.
Recommend performing this exercise as a class/group exercise. Talk about the corporate picnic or the youth food drive included in the Project Management Skills for Life document or another project and talk about “writing a project charter.” Ask what information is missing and not answered by the below questions.
Why is the project being initiated?
Who is this work being done for? Who are the project sponsor and the project stakeholders that might use the final product, service, or results?
What are we going to deliver? What work doe we need to complete; what resources and funds do we need to produce these deliverables?
When will we produce these deliverables? When will the stakeholders review them? When will the project sponsor approve and accept the final project outcome?
Where will the deliverables be used?
How are we going to achieve the project’s goal and objectives? How will success be measured?

## Slide 31: CHAPTER 2: Planning PROCESS

## Slide 32: Planning Process
The planning process involves organizing and identifying the components of a project.
The project manager and the project team work together to develop the scope of work, create a work breakdown structure, identify resources, estimate time needed to accomplish tasks, and recommend major deliverables.
Notes: Instructor’s Notes
PMBOK Terms and Definitions
Scope Statement – provides a documented basis for making any future decisions about the project and the approval from the stakeholders.
Work Breakdown Structure – a list of identified tasks to accomplish the project objectives and deliverables. The team prioritizes the task in order of completion. It helps to organize tasks into smaller work packages.
Project Schedule – the planned dates for performing schedule activities and planned dates for meeting schedule milestones.
Project Quality – the degree to which a set of inherent characteristics fulfills requirements.
Quality Planning – The process of identifying which quality standards are relevant to the project and determine how to satisfy them.
Project Communications – a process through which information is exchanged among persons using a common system of symbols, signs or behaviors.
Communication Planning – the process of determining the information and communications needs of the project stakeholder: who they are, what is their level of interest and influence on the project, who needs what information, when will they need it and how it will be given to them.
Project Risks – an uncertain event or condition that, if it occurs has a positive or negative effect on the project objectives.
Risk Identification – the process of determining which risks might affect the project and document their characteristics.
Project Procurement Documents – these documents are prepared either by the supplier or the sponsor for the bid and proposal activities.

## Slide 33: Scope Statement
Clarifies and expands the information in the project charter and adds:
Constraints
Assumptions
Risks
Boundaries (what will and will not be included)
User acceptance criteria
Notes: Instructor’s Notes
Talk about how the scope statement builds upon the project charter. Explain that both the project charter and scope statement should be written so that they are clear, concise and in non-technical terms .
Discuss why and how there might be changes to the project description and add additional deliverables. Include the below scope statement criteria into the document:
constraints
assumptions
boundaries (what will and will not be included)
risks
user acceptance criteria
Explain:
Project constraints are any factors that affect an activity or the schedule.
Project assumptions are considered true, real or certain. Assumptions sometimes involve risks associated with them.
Project risks are uncertain events or conditions that may have a positive or negative impact on project objectives.

## Slide 34: Project Scope
Defines the project parameters and establishes the baseline for measuring success
Provides a common understanding of project expectations

## Slide 35: Scope Statement
Exercise 4: Write a Scope Statement
Notes: Instructor’s Notes
Exercise 4: This exercise can be found in the Project Management Skills for Life document . Use the answers to exercise 3 to complete this exercise. Discuss with the team how the information in the project charter is expanded to create a scope statement. Allow 15 minutes for this group exercise.
Objective: Use the project charter that was completed in Exercise 3 to create a scope statement.
Divide the class into groups/teams
Use the project charter that was completed in Exercise 3
Have the team appoint a project manager for this exercise; that person will present findings
Review the project charter and have each group/team write a Scope Statement
Provide feedback on the responses.
Discuss how the additional information can impact the project outcome and is important to the planning process.

## Slide 36: Project Work Breakdown Schedule (WBS)
The work breakdown structure (WBS) is a checklist of all the work—the deliverables and tasks—prioritized in order of completion.
How to create a WBS:
Identify tasks or activities
Put tasks in order of completion
Identify deliverables and milestones
Notes: Instructor’s Notes
Refer to the Project Plan Template in the Appendix.

## Slide 37: Class Exercise
Create a Project Work Breakdown Structure
Project
Design Product
Develop Product
Test Product
Install Product
Notes: Instructor’s Notes
This exercise is not included in the Project Management Skills for Life document but can use the corporate picnic or youth food drive projects, or another project of your choosing. The work for one deliverable (such as the corporate picnic’s location deliverable or the youth food drive’s boxes deliverable) should be discussed prior to starting this exercise. Allow 20 minutes for this exercise.
Exercise: Create a work breakdown structure for the corporate picnic, food drive, or another project.
Objective: Learn how to create a work breakdown structure
Perform this exercise with the class.
Appoint someone to document the results.
Bring sticky pads and distribute them to each person, or use a flipchart or whiteboard. Someone could write down responses if sticky pads are not available.
Individuals begin writing tasks that need to be accomplished.
If time is limited the project manager could come up with a list and then the team could add additional tasks.
Show how the tasks can be divided to the lowest level.
Review the tasks and discuss any other deliverables and related work necessary to produce the final outcome.

## Slide 38: Project Schedule
Good planning allows the project manager to manage and control the project tasks and resources
The project schedule is developed by determining how long each task will take and assigning a resource to be responsible for the task
The team and project manager should divide the tasks and provide an estimate of the time required to complete each task
Notes: Instructor’s Notes
Stress the importance of good planning and allow enough time to discuss all aspects of the project.

## Slide 39: Project Schedule
Discussion: How to Estimate Tasks
Notes: Instructor’s Notes
Discuss with the team how to estimate tasks
After assigning tasks ask the team members how much time they would need to complete their tasks. You may have to make adjustments according to the end date of the project if it has already been set.
It is difficult to estimate tasks so you may wish to add some extra time to ensure they will be completed on time. This should be discussed with the team and there should be realistic expectations. Prepare for any unknown risks in the overall project schedule.

## Slide 40: Critical Path Method (CPM)
The critical path is the sequence of tasks that requires the longest duration to complete with no extra time.
The diagram on the next slide shows six tasks in the project schedule. Tasks A, C, and F are on the critical path, which means if one of these tasks takes longer than expected, the project will not meet the deadline.
Notes: Instructor’s Notes

## Slide 41: Critical Path Method (CPM)
Task A took longer than expected, which affected when Tasks C & F could start, and added 1.5 weeks to the original schedule.
WEEK 1
WEEK 2
WEEK 3
WEEK 4
WEEK 5
WEEK 6
WEEK 7
TASK A
TASK B
TASK F
TASK E
TASK D
TASK C

## Slide 42: Class Exercise
Create a Project Schedule
Notes: Instructor’s Notes
This exercise is not in the Project Management Skills for Life document, but it uses the Project Plan Template in the Appendix.
Exercise: Create a project schedule for the corporate picnic, food drive, or another project that was identified in the prior class exercise.
Objective: Learn how to create a project schedule.
Now that the tasks are identified, add the timeframes, resources and major deliverables.
Divide into teams or work as a group.
Determine the expected start and end dates.
Identify the resources responsible for the tasks and deliverables.
Review any risks or notes associated with the project noted in the project charter document.
Use the Project Plan Template in the Appendix to record the information from the WBS exercise and this exercise.

## Slide 43: Project Quality
Ensure stakeholder expectations are being met by defining processes to verify and validate successful product completion.
Understanding the desired outcome allows the team to work together to build quality into the product.
Monitor quality throughout the project.

## Slide 44: Project Communication
Develop a plan that answers the following questions: What, When, Who, Where and How:
What needs to be communicated?
When does the information need to be distributed?
Who should receive the information (all stakeholders)?
Where should the information be distributed?
How and in what format should the information be presented?
Notes: Instructor’s Notes
One of the most important components of a project is implementing a solid communication plan.
As a group, answer the questions listed on the slide.

## Slide 45: Communication
The Sender-Receiver Model
The sender sends a message without interruptions or distractions. The receiver selects an approach that is acceptable to the team and is available to all members.
Process Steps
Sender has an idea to communicate
Sender selects the approach (voice, gesture, symbols, email, phone or meetings)
Is there any noise that affects or impedes the message?
Receiver processes the information sent by sender
Receiver responds to message with appropriate approach
Notes: Instructor’s Notes
Use the model to understand why sending and receiving information needs to be clear and free from any interruptions or distractions.
Explain the steps in this Sender-Receiver Model process.

## Slide 46: Project Status Report
Project status reports are completed by the project manager on a regular basis.
Components of the Project Status Report:
Project Title
Project Manager
Report Date
Current Status
Activities completed during this period
Activities to be accomplished by the next meeting
Issues and Resolutions
Changes to project scope
Problems, Risks or Concerns
Notes: Instructor’s Notes
Explain the components of the status report.

## Slide 47: Successful Meetings
Tips for Conducting Successful Meetings:
Determine meeting place and time
Conduct the meeting with an agenda
Ask all members to report their status on tasks
Identify any new risks or issues
Discuss solutions to issues
Ask members if they will meet their task deadlines
End each meeting on time and announce the next meeting
Send out meeting minutes
Notes: Instructor’s Notes
Explain why conducting successful meetings is critical to the process. Research indicates people don’t want to waste time and want to accomplish project goals or have effective discussions. Use these tips to conduct productive meetings.

## Slide 48: Project Risks
Discussion: Identify, document, and examine project risks
Notes: Instructor’s Notes
The project manager should conduct a meeting with the team to identify possible risks that could occur during the development of the product or service.
The team identifies risks early in the project and develops a plan to mitigate any risks.
Monitor continually throughout the project.

## Slide 49: Project Procurement
Create a plan to monitor any changes to contracts that occur during the project
The project manager will need to understand the contract requirements
All contracts are closed at project completion
Notes: Instructor’s Notes
The project manager should monitor any contracts with vendors and suppliers. If there is someone monitoring the budget, that person could be in charge of these contracts too.
Use the sponsor and/or legal assistance to review these documents prior to engaging or signing the contracts.

## Slide 50: CHAPTER 3: EXECUTING PROCESS

## Slide 51: Executing Process
The planning is now complete and the team can begin working on assigned tasks.
Project status reporting will be conducted on a regular basis.
Any issues that arise will be discussed with the team and sponsor.
Some tasks may be re-assigned individuals cannot complete them on time or require extra assistance.
The project manager will need to monitor and control the tasks to ensure timely completion.
Communication is ongoing during this phase.
Notes: Instructor’s Notes
Explain the executing process
The team has completed the planning process and work can now begin.
Regular status reporting and meetings to discuss the progress will occur during this process.
Continue to nourish open communication among team members, stakeholders and the project manager.
PMBOK Terms and Definitions
Project Executing – This process is when the work defined in the planning is started. The scope statement explain the objective or purpose for the project.
Issue – something in question or in dispute that needs to be resolved for the project to proceed.
Change Request – Requests to expand or reduce the project scope or procedures. Usually only formal documented request changes are performed with signed approval.

## Slide 52: Executing Process
Recommendations for Procuring Resources:
Understand the requirements of the product or services
Follow a process for soliciting bids
Negotiate terms with vendors or suppliers and have a legal expert review the contractual agreement
Implement a billing and payment plan
The project manager and team should ensure the quality requirements are being met
Notes: Instructor’s Notes
Review the recommendations Explain that it is important to follow the procedure for your organization, but these recommendations can be used as guidelines.

## Slide 53: CHAPTER 4: MONITORING AND CONTROLLING PROCESS

## Slide 54: Monitoring and Controlling Process
Review and track the progress of the project
Manage project issues and change requests
Review the scope statement periodically to ensure objectives are being met
Obtain sponsor sign-off if changes are made to the project’s scope
Notes: Instructor’s Notes
Explain that the monitoring and controlling process involves measuring and monitoring project execution and taking corrective action to keep the project on track according to the objectives of the project.
Explain the importance of reviewing the scope statement throughout all phases of the project.
Refer to the Issue Log Template and Change Request Template in the Appendix.

## Slide 55: What Is…
What is the issue log?
What is the change request log?
Notes: Instructor’s Notes
Refer to the Issue Log Template in the Appendix
Discuss the need for an Issue Log and how an issue can become a change request:
Number
Issue
Owner
Status
Date Opened
Date Closed
Resolution

## Slide 56: Change Control
Exercise and Discussion
Notes: Instructor Notes
Exercise 5: This exercise can be found in the Project Management Skills for Life document. Discuss with the team how an unexpected change can impact a project. Allow 10 minutes for this exercise
Objective: Discuss the impacts of change and the importance of controlling change throughout the project.
Questions to discuss:
How did the changes impact the scope and/or schedule of the project?
What could happen to a project to cause the project schedule to slip or incur scope creep?
Scope creep is added work without appropriately adjusting schedules and resources and without obtaining approval of the sponsor.

## Slide 57: On-Going Activities
The following activities, already covered, are on-going activities that are completed throughout the project:
Time Management
Communication
Managing risks
Controlling the schedule
Monitoring the budget
Notes: Instructor’s Notes
Explain that the project manager and team need to watch these on-going activities throughout the project.
Be prepared to discuss with the group.

## Slide 58: CHAPTER 5: CLOSING

## Slide 59: Closing Process
This is the end of the project and these activities are conducted:
Lessons learned
Final work
Contract closeout
Notes: Instructor’s Notes
The closing process is a formal termination of the project activities.
PMBOK Terms and Definitions
Project closing – this is the process to formally terminate all activities of a project or phase.
Lessons learned – This is an open meeting to discuss any changes that could help improve future projects.
Contract closure – the process of completing any contracts and obtaining appropriate sign-off.

## Slide 60: Lessons Learned
Discussion: What were the successes and failures of the project?
Notes: Instructor’s Notes
Lessons Learned
Explain the lessons learned process. Have the team discuss the successes and failures of the project. Record the responses in the Lessons Learned Template in the Appendix.

## Slide 61: Final Work
Complete any paperwork and all documentation for the project
Assign a person who will keep the records as a reference for similar future project work
Notes: Instructor’s Notes
Final Work
Complete all forms and inform the team of project closure. Prepare to hand the product or service to the sponsor. Document any records or files.

## Slide 62: Contract Closeout
Complete all paperwork and contracts associated with the project
Obtain approval from the sponsor
Notes: Instructor’s Notes
Contract Closeout
Actually prepare to transfer the product or service to the sponsor (this could be a client or customer.) Follow up with the sponsor to ensure the requirements were met.

## Slide 63: Celebrate! Celebrate! Celebrate!
Discussion: Celebrating the conclusion of the project
Notes: Instructor’s Notes
Discuss how to celebrate the completion of the project. Explain how celebrating builds good synergy among team members and allows for networking.
Use examples of your own to describe ways to get the team together.
Be creative to show appreciation for the team members.
The project manager or the team can decide how to celebrate the closure of the project.

## Slide 64: SUMMARY AND REVIEW

## Slide 65: Summary and Review
Defining project management and projects
Identifying the five process groups
Describing the roles of team members and how they interact during a project
Writing a project charter and scope statement
Creating a project plan—work breakdown structure, schedule, resources and the critical path
Understanding potential project risks
Building quality into the project
Procuring products and services
Communicating from project start to completion
Monitoring, tracking, and reporting on the project’s progress
Training and mentoring team members

## Slide 66: Summary and Review
A Project:
Is a temporary endeavor with a definite beginning and end
Creates or produces a unique product, service, or result
Notes: Instructor’s Notes
Emphasize the requirements of a project

## Slide 67: Summary and Review
You are now aware of the five processes commonly used to manage projects:
Initiating
Planning
Executing
Monitoring and Controlling
Closing
Notes: Instructor’s Notes
Discuss the five processes – see if the students can recite them in order.

## Slide 68: Summary and Review
The following basic questions should be answered when starting any project:
What are you going to deliver or accomplish?
When will you produce deliverables?
Who are your stakeholders (customers, sponsors, end users, team members)?
Why is the work necessary?
Where will the project outcomes be used, delivered, or built when appropriate?
How will you accomplish and manage the objectives? How will you measure success?
Notes: Instructor’s Notes
Review the questions and recap the importance of getting them right before the work begins.

## Slide 69: Summary and Review
It is important to train and mentor the individuals involved in the project.
It is extremely important to communicate with all stakeholders throughout the process, and to document and share information regarding the status of the project.
Without communication you cannot be successful.
Ensure that any contractual agreements used during the project are closed, and that all appropriate invoices are processed for final payment.
Notes: Instructor’s Notes
Talk and discuss:
any mentoring and coaching experiences, particularly how mentoring and coaching assisted with the completion of tasks.
how communication is so critical during the entire lifecycle of a project
an example of closing a contractual agreement

## Slide 70: Summary and Review
Project Sponsors typically take responsibility for signing off on the completion of all agreed upon work.
Other stakeholders may also wish to be involved in the signoff process.
Notes: Instructor’s Notes
Why is having sign-off from the sponsor needed?

## Slide 71: QUESTIONS?

## Slide 72: PLEASE COMPLETE THE TRAINING EVALUATION AND RETURN TO THE INSTRUCTOR

## Slide 73: Thank you
Contact name
Title
  Email phone or address